## Planned Objects
A plan of the object to develop in the Sprint
Object | Type | Link to Specification | Developer | Due Date | Sprint | Ready pct | Dev Comment | PM Comment
Internet Sales | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii Razumov | 2022-08-30 | 1,2,3 | 0.85 | Waiting for data validation from EDA
Internet Sales Amount | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii Razumov | 2022-08-30 | 3 | 0.3
Custom Sales | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii Razumov | 2022-08-30 | 2,3 | 0.5
Custom Sales Amount | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii Razumov | 2022-08-30
Custom Sales Quantity | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii Razumov | 2022-08-30