## Planned Objects
A plan of the object to develop in the Sprint
01_Object Name | 02_Type | 03_Link to Specification | 04_Developer | 05_Tasks | 06_Due Date | 07_Sprint | 08_Status | 09_Ready for pct | 10_Dev Comment | 11_PM Comment
Internet Sales | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-01, JR-15, JR-16/1 | 2022-08-30 | 1,2,3 | On Hold | 0.85 | Waiting for data validation from EDA
Internet Sales Amount | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-02 | 2022-08-30 | 3 | On Hold | 0.3
Custom Sales | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-03 | 2022-08-30 | 2,3 | On Hold | 0.5 | Some clarification is required!
Custom Sales Amount | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-04 | 2022-08-30 |  | To Start
Custom Sales Quantity | Measure | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-05 | 2022-08-30 |  | To Start
Customer | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-06 | 2022-08-30 | 3 | UAT | 0.95 | implementing User Remarks
Product | Table | https://onedrive.live.com/view.aspx?resid=43FC8CA3B17868DD%21806&id=documents&wd=target%28VS%20Code.one%7C062DAB10-4A3E-4127-8D96-1AB4A4286FC7%2FDummyTask%3A%20Add%20Internet-Sales%7CC38A5B3B-DB39-4862-8800-09D041CB42B0%2F%29 | Sergii_Razumov@epam.com | JR-07 | 2022-08-30 | 3 | To Start |  | Waiting for specification
Custom Internet Sales | Table | NAN | NAN | NAN | NAN | 3 | Removed |  |  | Removed from project on [2022-08-25] according to FUp letter from <CustomerRepresentative>

## Team
Index | Property | Value | Email | StartDate | EndDate | Comment
1 | TL | Amade Wolfgang | some_sample@email.com | 2022-07-07
2 | BA | Ledowskykh Sergii | some_sample@email.com | 2022-07-07
3 | PO | Shelly Bengia | some_sample@email.com | 2022-07-07
4 | developer | Razumov Sergii | sergii_razumov@epam.com | 2022-07-07
5 | QA | Razumov Sergii | sergii_razumov@epam.com | 2022-07-07

## PrivelegedUsers
User | MergeMain
sergiy.razumov@gmail.com | TRUE
someemail@com | FALSE